## Online Media
| 2015-12-26 | 2016-01-02 | 2016-01-09 | 2016-01-16 | 2016-01-23 | 2016-01-30 | 2016-02-06 | 2016-02-13 | 2016-02-20 | 2016-02-27 | 2016-03-05 | 2016-03-12 | 2016-03-19 | 2016-03-26 | 2016-04-02 | 2016-04-09 | 2012-04-16 | 2016-04-23 | 2016-04-30 | 2016-05-07 | 2016-05-14 | 2016-05-21 | 2016-05-28 | 2016-06-04 | 2016-06-11 | 2016-06-17 |  | 6/21/2016 through 12/25/2016
| 24 weeks | 23 weeks | 22 weeks | 21 weeks | 20 weeks | 19 weeks | 18 weeks | 17 weeks | 16 weeks | 15 weeks | 14 weeks | 13 weeks | 12 weeks | 11 weeks | 10 weeks | 9 weeks | 8 weeks | 7 weeks | 6 weeks | 5 weeks | 4 weeks | 3 weeks | 2 weeks | 1 week! | 0 week! Event and post-event | 52 weeks |  | post-event lull
Social Media- Anna H
weekly posts to Facebook, Twitter, and blog | choose 3; use best pics from previous year | choose 2 or 3 days to post; use best pics from previous year | choose 3 | choose 3 | choose 2 or 3 days to post; use best pics from previous year | choose 2 or 3 days to post; use best pics from previous year | choose 2 or 3 days to post; use best pics from previous year | choose 2 or 3 days to post; use best pics from previous year | choose 2 or 3 days to post; use best pics from previous year | choose 2 or 3 days to post; use best pics from previous year | choose 2 or 3 days to post; use best pics from previous year | choose 2 or 3 days to post; use best pics from previous year | choose 2 or 3 days to post; use best pics from previous year | choose 2 or 3 days to post; use best pics from previous year | choose 2 or 3 days to post; use best pics from previous year | choose 2 or 3 days to post; use best pics from previous year | choose 2 or 3 days to post; use best pics from previous year | choose 2 or 3 days to post; use best pics from previous year | choose 2 or 3 days to post; use best pics from previous year | choose 2 or 3 days to post; use best pics from previous year | daily | daily | 3 x daily | 3 x daily | 3 x daily | daily |  | daily for a bout a week or so; then choose 2 or 3 days to post; use best pics from previous year
Monday- general announcement | [6 empty] | announce opening call for art |  |  |  |  | reiterate call for art / Season-long final week to submit | announce close CfA Season-long |  |  |  | announce 2 weeks until CfA closes |  | announce last day CfA |  | announce "Bring your project even if you are not registered" |  |  | announce 1 week to FIGMENT
Tuesday- open-ended question or quote-of-the-week (optional: as of 2013 season)
Wednesday- pic of the week
Thursday- answer-inspired post or community spotlight | [5 empty] | use writers effort; link to post/news |  |  |  | use writers effort; link to post/news |  |  |  | use writers effort; link to post/news |  |  |  |  | use writers effort; link to post/news |  |  |  | use writers effort; link to post/news
Friday- interview or quote
Website | archive previous year's site; prepare this year's site (web master) | start updating event info for current year as soon as info is available | start updating event info for current year as soon as info is available | welcome new team member at Kick off meeting; set expectations; find 25 previous FIGMENT artists willing to be interviewed and share doc with writer team | make sure call for art copy and artist tips&tricks guides are updated on site | call for art up on website; blog posts | All Calls for Art go out; announcement via blog |  | start building Groundbreaking page; use finalized design invite! (copy Carlijn, invite upload web master) Install shopping cart for tickets | Groundbreaking announced via blog posts | Call for Art season-long extended; blog posts; build Groundbreaking catalog | Call for Art season-long last week to submit | cfa season-long submissions closed: take down pages; blog posts |  | reminder Groundbreaking + weekend event submissions + submissions Pavilion; blog post refresh | Pavilion submissions closed; take down page, blog post; build pages season-long Minigolf and Sculpture Garden. Make sure public description is perfect and double-checked; needed for season-long signs |  |  | CfA for event closed; take down page; replace copy with generic "see you there!" | finalize public descriptions of registered projects via curatorial; with help of curatorial, choose 8-10 projects to highlight in press release and press package | put up artists + projects page; highlight columns in google dco you want online; extract info from google docs to site; web master knows how to do it! Start compiling press package; put online and print for event | update artists + projects page with new info via curatorial | update artists + projects page with new info via curatorial | update artists + projects page with new info via curatorial | big thank you post; update images for pages with this year's photos | update site where needed; update rpess page |  | update photo gallery with this year's best of pics; post whenever something interesting happens
writers/interviewers | monthly per writer |  |  |  |  | Post to blog/news |  |  |  | Post to blog/news |  |  |  | Post to blog/news |  |  |  |  | Post to blog/news |  |  |  | Post to blog/news
- look at event calendar, choose 2 events per month to attend and write-up, choose 1 artist per month to interview and write-up or film | [5 empty] | 1 event write-up and 2 interviews due |  |  |  | 1 event write-up and 2 interviews due |  |  |  | 1 event write-up and 2 interviews due |  |  |  |  | 2 event write-ups and 1 interview due |  |  |  | 2 event write-ups and 1 interview due
Newsletters | merry christmas / happy new year from FIGMENT |  |  | kick off meeting; welcome to the new FIGMENT year! |  |  | CfA announcement |  |  | GB announcement; Reminder season-long deadline NYC CfA, Weekend CfA, and GB tickets for sale | CfA extension announcement | CfA deadline reminder |  |  | reminder Groundbreaking + weekend event submissions + submissions Pavilion | announce winners of season-long calls for art (minigolf + sculpture garden) |  |  | CfA event closes |  | announce bring your project! | announce event | announce event | announce event | big thank you newsblast |  |  | Other events coming up; Thanksgiving with FIGMENT;
Press |  |  |  |  | draft press release announcing call for art / event | finalize press release | official press release announcement all calls for art | draft press release announcing groundbreaking | finalize press release | official PR for Groundbreaking event |  |  |  | draft press release announcing season-long projects | finalize press release with winning projects/proposals | official press release announcing season-long projects Sculpture garden | official press release announcing season-long projects Minigolf |  | draft press release announcing event | finalize press release with highlighted art projects | official press release announcing FIGMENT event; highlight some art! |  |  |  |  | draft press release pavilion |  | official press release for 2012-2013 pavilion!
press package | [19 empty] | start compiling press package | finalize press package | communicate with press; have pics at the ready and be ready for fact-check; set up press dates for interviews and/or camera crews | communicate with press; have pics at the ready and be ready for fact-check; set up press dates for interviews and/or camera crews | communicate with press; have pics at the ready and be ready for fact-check; set up press dates for interviews and/or camera crews | communicate with press; have pics at the ready and be ready for fact-check; set up press dates for interviews and/or camera crews |  |  | communicate with press; have pics at the ready
Signage |  |  |  | find builders/helpers to construct signs for event | [5 empty] | start thinking about what type of signs you want and how many, how to brand, where to put directional / area signs at venue | [5 empty] | design season-long signs for minigolf and sculpture garden; get copy from Carlijn |  | finalize signage plan: number, type and placement of signs at venue | finalize budget for building signs | start building signs | start building signs; design season-long signs and have approved by Branding via Carlijn | start building signs; deliver season-long designs to PRINTER | start building signs | finish building signs; pick up printed season-long signs at printer and install season-long signs | take down | sleep
4 Welcome to FIGMENT banners on high frame (island x2; ferry terminal x2) | [9 empty] | material needs? Banner material, wood, nails; an artist to design? | [9 empty] | build | build | build | build | install signs at venue | take down
6 area sandwich boards | [9 empty] | material needs? plywood, paint, hinges | [9 empty] | build | build | build | build | install signs at venue | take down
5 directional sandwich boards | [9 empty] | material needs? plywood, paint, hinges | [9 empty] | build | build | build | build | install signs at venue | take down
season-long signs for minigolf and sculpture garden | [9 empty] | material needs? Tyvek, box signs, minigolf flag signs, nails, paint | [5 empty] | design season-long signs by Ken and Johnny; design approval by Smash; copy provided by Carlijn; double check by Carlijn and SL curators Jacquie, CJ and Katherine |  |  |  | build | build | build | build | install signs at venue | take down
placement markers for artists | [9 empty] | material needs? Paint sticks and staple gun | [13 empty] | install temporary placement markers at venue | take down
11 principles of FIGMENT | [9 empty] | material needs? | [9 empty] | build | build | build | build | install signs at venue | take down
3 stage signs | [9 empty] | material needs? | [9 empty] | build | build | build | build | install signs at venue | take down
Promotional/print material - Design Team |  |  | finalize budget
event postcards (FIGMENT INC) |  |  | finalize budget | design | design | draft ready | finalized design ready to print |  |  | printed and ready for distribution |  |  |  |  | ask for shipment and distribute!
event posters (FIGMENT INC |  |  | finalize budget | design | design | draft ready | finalized design ready to print |  |  | printed and ready for distribution |  |  |  |  | ask for shipment and distribute!
event T-shirts (FIGMENT INC) |  |  | finalize budget | [18 empty] | ask for shipment and distribute!
Groundbreaking invite (Ken) |  |  | finalize budget |  |  | design | draft ready | finalized design ready to print |  | printed and ready for distribution
season-long signs for minigolf and sculpture garden (Ken and Johnny) |  |  | estimate budget based on previous year | [6 empty] | sculpture garden tyvek 17x22; minigolf tyvek triangle Y x 22 folded | [7 empty] | ask printer for quote based on number of signs, specs and materials | design season-long signs by Ken and Johnny; design approval by Smash; copy provided by Carlijn; double check by Carljin and SL curators Jacquie, CJ and Katherine | finalize designs |  | designs print-ready and sent to printer |  | pick up printed signs at printer and install
season-long poster (Ken) | [9 empty] | paper laminated 11x17 | [14 empty] | design season-long posters by Ken with this year's best pics selection; print and put on ferries | design season-long posters by Ken with this year's best pics selection; print and put on ferries | design season-long posters by Ken with this year's best pics selection; print and put on ferries
Photography / videography (Tes) |  |  | make sure to include email address online (event info) for amateur photographers to send their images to! | [16 empty] | Guidelines: glamorous, people interacting with the art, detail or wide shot, landscape format (not portrait), diversity of people (young, old, all ethnicities) and diversity of projects. Idea: hand out different projects to highlight to different photographers so they don't all take pics of the same project | reach out to professional photographers' and videographersnetwork to document event; send photographers agreement | reach out to professional photographers' and videographersnetwork to document event; send photographers agreement | reach out to professional photographers' and videographersnetwork to document event; send photographers agreement | reach out to professional photographers' and videographersnetwork to document event; send photographers agreement | Take pictures of ALL finalized and installed season-long projects! Site pages need to be updated with actual images asap. ALSO: upload top-5/10 of high-quality images of event to gallery for press distribution. IDEALLY done during event!! | roam Flickr and FTP for best shots; make first selection of best-of | Sort best-of folder of pictures of ALL event and season-long projects! Site pages and gallery need to be updated with actual images asap. ALSO: sort and put up any videos on FIGMENT Youtube page | Sort best-of folder of pictures of ALL event and season-long projects! Site pages and gallery need to be updated with actual images asap. ALSO: sort and put up any videos on FIGMENT Youtube page
Outreach - Audrey |  |  |  | as soon as website is updated for current year, start outreach | outreach email | follow-up by phone | outreach email | follow-up by phone | outreach email | follow-up by phone | outreach email | follow-up by phone | outreach email | follow-up by phone | outreach email | follow-up by phone | outreach email | follow-up by phone | outreach email | follow-up by phone | outreach email | follow-up by phone | outreach email | follow-up by phone
Education - Kate

## Print Media
| 2012-12-26 | 2012-01-02 | 2012-01-09 | 2012-01-16 | 2012-01-23 | 2012-01-30 | 2012-02-06 | 2012-02-13 | 2012-02-20 | 2012-02-27 | 2012-03-05 | 2012-03-12 | 2012-03-19 | 2012-03-26 | 2012-04-02 | 2012-04-09 | 2012-04-16 | 2012-04-23 | 2012-04-30 | 2012-05-07 | 2012-05-14 | 2012-05-21 | 2012-05-28 | 2012-06-04
| 24 weeks | 23 weeks | 22 weeks | 21 weeks | 20 weeks | 19 weeks | 18 weeks | 17 weeks | 16 weeks | 15 weeks | 14 weeks | 13 weeks | 12 weeks | 11 weeks | 10 weeks | 9 weeks | 8 weeks | 7 weeks | 6 weeks | 5 weeks | 4 weeks | 3 weeks | 2 weeks | 1 week!
Postcards/Posters
Groundbreaking
Scheduling- Event
Season-long Signage
Event Signage

## Archive_Documentation
2012-12-26 | 2012-01-02 | 2012-01-09 | 2012-01-16 | 2012-01-23 | 2012-01-30 | 2012-02-06 | 2012-02-13 | 2012-02-20 | 2012-02-27 | 2012-03-05 | 2012-03-12 | 2012-03-19 | 2012-03-26 | 2012-04-02 | 2012-04-09 | 2012-04-16 | 2012-04-23 | 2012-04-30 | 2012-05-07 | 2012-05-14 | 2012-05-21 | 2012-05-28 | 2012-06-04
24 weeks | 23 weeks | 22 weeks | 21 weeks | 20 weeks | 19 weeks | 18 weeks | 17 weeks | 16 weeks | 15 weeks | 14 weeks | 13 weeks | 12 weeks | 11 weeks | 10 weeks | 9 weeks | 8 weeks | 7 weeks | 6 weeks | 5 weeks | 4 weeks | 3 weeks | 2 weeks | 1 week!

## Education
2012-12-26 | 2012-01-02 | 2012-01-09 | 2012-01-16 | 2012-01-23 | 2012-01-30 | 2012-02-06 | 2012-02-13 | 2012-02-20 | 2012-02-27 | 2012-03-05 | 2012-03-12 | 2012-03-19 | 2012-03-26 | 2012-04-02 | 2012-04-09 | 2012-04-16 | 2012-04-23 | 2012-04-30 | 2012-05-07 | 2012-05-14 | 2012-05-21 | 2012-05-28 | 2012-06-04
24 weeks | 23 weeks | 22 weeks | 21 weeks | 20 weeks | 19 weeks | 18 weeks | 17 weeks | 16 weeks | 15 weeks | 14 weeks | 13 weeks | 12 weeks | 11 weeks | 10 weeks | 9 weeks | 8 weeks | 7 weeks | 6 weeks | 5 weeks | 4 weeks | 3 weeks | 2 weeks | 1 week!

## LeaveNoTrace
2012-12-26 | 2012-01-02 | 2012-01-09 | 2012-01-16 | 2012-01-23 | 2012-01-30 | 2012-02-06 | 2012-02-13 | 2012-02-20 | 2012-02-27 | 2012-03-05 | 2012-03-12 | 2012-03-19 | 2012-03-26 | 2012-04-02 | 2012-04-09 | 2012-04-16 | 2012-04-23 | 2012-04-30 | 2012-05-07 | 2012-05-14 | 2012-05-21 | 2012-05-28 | 2012-06-04
24 weeks | 23 weeks | 22 weeks | 21 weeks | 20 weeks | 19 weeks | 18 weeks | 17 weeks | 16 weeks | 15 weeks | 14 weeks | 13 weeks | 12 weeks | 11 weeks | 10 weeks | 9 weeks | 8 weeks | 7 weeks | 6 weeks | 5 weeks | 4 weeks | 3 weeks | 2 weeks | 1 week!